## Sheet1
RiskID | Date Raised | Risk Description | Likelihood | Impact | Severity | Owner | Mitigating or Corrective Action | Observed Results | Progress on Actions | Date Resolved | Status
| 2021-10-03 | Attacker gains access to the database | Medium | High | Medium | DBA | Deploy Web App FireWall
| 2021-10-03 | Headquarters burns down | Low | High | Medium | Facilities | Purchase Insurance and setup offsite backup |  |  |  |  | Levels | No Significant | Low Significant | Moderate | Critical | Catastrophic
| 2021-10-03 | Employee accidently deletes data | High | High | High | DevOps | Configure backup and story policieis |  |  |  |  | Define | High | High | Elevated | Elevated | Elevated
| 2021-10-03 | Sensitive documents leak online | Medium | High | Medium | Security | Parameter scanning and daata exfiltration software |  |  |  |  | Likely | Medium | High | High | Elevated | Elevated
| 2021-10-03 | Unauthorized user reboots device | Medium | Medium | Medium | DevOps | Extend auditing policy |  |  |  |  | Occasional | Low | Medium | High | Elevated | Elevated
| 2021-10-03 | Foreign advisary steals IP | Medium | High | High | Security | Work with compliance and marketing to determine international release schedules |  |  |  |  | Seldom | Low | Low | Medium | High | Elevated
| 2021-10-03 | Middle management blocks collaboration adoption | Medium | High | High | Execs | Define organizational norms and reporting infrastructure |  |  |  |  | Unlikely | Low | Low | Medium | High | High
| 2021-10-03 | Support tickets cannot route efficiently | High | High | High | DevOps | Define policies for integrating new processes with existing incident responses
| 2021-10-03 | Security team creates unnecessary roadblocks | High | High | High | Execs | Establish Technical Community with cross disopline membership
| 2021-10-03 | DevOps teams implement incomplete protections | Medium | Medium | Medium | Security | Create a well-defined toolset of common security tools